Action Plan

Instructions: Click on a field (gray area) and begin typing to complete that field. To go to the next field, push the Tab button. When you are finished, you can save or print your completed form.

| Learner: Mary Danso Training Intervention: Family Planning/Counseling Update Date: April 01 |  |  |  |  |
| --- | --- | --- | --- | --- |
| My Support Team/Network Supervisor: Mrs. Nyako Trainer: Miss Zakari Co-worker(s): Fatou Abudu (attended training with Mary), Doris Isa, Mercy Nunoo, Awa Koufi |  |  |  |  |
| Specific Areas to Improve: I want to improve my ability to provide appropriate counseling about FP methods (Think about distinct accomplishments and activities to be achieved.) |  |  |  |  |
| Problems to Overcome: Don't have a setting for confidential conversations - identify and discuss possible options with clinic supervisor (Describe the barriers that must be eliminated or reduced and how this will be done.) |  |  |  |  |
| Detailed Specific Actions in Sequence (Include regular progress reviews with the support team as a part of the specific actions.) | Responsible Person(s) | Resources | Date/Time* | Changes to Look For |
| Step 1. Participate in post-training meeting to review, revise and endorse my action plan (and Fatou's); compare with/update procedures manual as needed (follow-up to pre-training meeting) | Entire support team | action plans; procedures manual | May 1 2pm | plans and manual complementary; team's roles/actions clarified |
| Step 2. Rearrange furniture in the clinic supervisor's office to create small private area for counseling | Mary, Fatou | chairs & table | May 2 2pm | staff using space appropriately |
| Step 3. Assemble box of FP method samples to use during counseling sessions (store on shelf in counseling area for all providers to use) | Doris, Mercy | box & supplies from stock | May 2 2pm | samples always ready to use |
| Step 4. Create poster that encourages clients to ask their provider about FP; hang in waiting area | Mary, Fatou | poster board & markers | May 3 2pm | clients reading poster and asking questions |
| Step 5. Review counseling job aid and notes from training activity; place job aid on table in counseling area | Mary | job aid from training | May 3 2pm | feel ready for practice session |
| Step 6. Conduct a practice counseling session with co-worker in counseling area, using FP samples and job aid | Mary, Awa | counseling area; samples; job aid | May 4 2pm | build confidence; ensure suitability of space design |
| Step 7. Observe and provide feedback during practice counseling session (Fatou to practice as well) | Fatou, Mrs. Nyako | counseling skills checklist | May 4 2pm | useful feedback (peer/supervisor) |
| Step 8. Participate in action plan review session; revise and/or update plan depending on progress to date | Entire team | action plan | May 7 2pm | team agrees that I'm ready to counsel clients |
| Step 9. Orient clients and counsel those interested in FP; document issues/questions in learning journal | Mary | learning journal | May 11 ongoing* | increase in clients choosing an FP method |
| Step 10. Discuss journal entries with co-workers (and with supervisor as needed) | all peers | learning journal | ongoing* | insights regarding improvements |
| Step 11. Observe counseling session and provide feedback (Fatou to be rated as well) | Mary, Mrs. Nyako | skills checklist | ongoing* | ensure proficiency matches standard |
| Commitment of Support Team/Network: I support the action plan described above and will complete the actions assigned to me. If I am unable to complete an activity, I will help make arrangements to modify the plan accordingly. |  |  |  |  |
| Signature of Learner: Mary Danso Date: May 3, 2001 Signature of Supervisor: Nana Nyako Signature of Trainer: Aby Zakari Signature of Co-workers: Fatou Abudu, Doris Isa, Mercy Nunoo, Awa Koufi |  |  |  |  |

*Establish set day and time for ongoing activities.